## part a
Problem : Project Scheduling
| Task Number | Minimum Time | Standard Time | Standard Cost | Cost/Day to Shorten | Predecessor Tasks
| 1 | 6 | 12 | 1600 | 100 | None
| 2 | 8 | 16 | 2400 | 75 | None
| 3 | 16 | 24 | 2900 | 120 | 2
| 4 | 14 | 20 | 1900 | 100 | 1,2
| 5 | 14 | 16 | 3800 | 140 | 3
| 6 | 12 | 16 | 2900 | 165 | 3
| 7 | 2 | 12 | 1300 | 60 | 4
|  |  |  | Task Number | 1 |  | Task Number | 4 |  | Task Number | 7
|  |  |  | Days (number) | 12 |  | Days (number) | 20 |  | Days (number) | 12
|  |  |  | ES | 0 |  | ES | 16 |  | ES | 36
|  |  |  | LS | 12 |  | LS | 24 |  | LS | 44
| Task Number | Start |  | slack variable | 12 |  | slack variable | 8 |  | slack variable | 8 | Task Number | Finish
| Days (number) | 0 |  | crash (day) | 6 |  | crash (day) | 6 |  | crash (day) | 10 | Days (number)
| ES | 0 |  | cost | 100 |  | cost | 100 |  | cost | 60 | ES | 56
| LS | 0 | [9 empty] | LS | 56
| slack variable | 0 | [7 empty] | Task Number | 5 | slack | 0
|  |  |  | Task Number | 2 |  |  | Task Number | 3 | Days (number) | 16 | goal | 40
|  |  |  | Days (number) | 16 |  |  | Days (number) | 24 | ES | 40 | crash | -16
|  |  |  | ES | 0 |  |  | ES | 16 | LS | 40
|  |  |  | LS | 0 |  |  | LS | 16 | slack variable | 0
|  |  |  | slack variable | 0 |  |  | slack variable | 0 | crash (day) | 2
|  |  |  | crash (day) | 8 |  |  | crash (day) | 8 | cost | 140
|  |  |  | cost | 75 |  |  | cost | 120
[10 empty] | Task Number | 6
[10 empty] | Days (number) | 16
| Paths | Days | Goal | [6 empty] | ES | 40
| A(1-4-7) | 44 | -4 | [6 empty] | LS | 40
| B(2-4-7) | 48 | -8 | [6 empty] | slack variable | 0
| C(2-3-5) | 56 | -16 | [6 empty] | crash (day) | 4
| D(2-3-6) | 56 | -16 | [6 empty] | cost | 165
| Number Crashing Total Cost | 16800
| Completion Days | 56

## part b
This is the task table
Task
| 1 | 2 | 3 | 4 | 5 | 6 | 7
| 0 | 8 | 8 | 0 | 0 | 0 | 4 |  |  | Normal Cost | $16,800.00
[10 empty] | Days Crashed | 20
Duration (days) | 12 | 16 | 24 | 20 | 16 | 16 | 12 |  |  | Min Crash cost | 1800
Crash Days | 6 | 8 | 8 | 6 | 2 | 4 | 10 |  |  | Min with crash cost | 18600
Crash Cost | 100 | 75 | 120 | 100 | 140 | 165 | 60
Normal Cost | 1600 | 2400 | 2900 | 1900 | 3800 | 2900 | 1300
Paths | [8 empty] | Path Duration
A | 1 | 0 | 0 | 1 | 0 | 0 | 1 |  | 40
B | 0 | 1 | 0 | 1 | 0 | 0 | 1 |  | 36
C | 0 | 1 | 1 | 0 | 1 | 0 | 0 |  | 40
D | 0 | 1 | 1 | 0 | 0 | 1 | 0 |  | 40
Goal | 40
[8 empty] | LHS |  | RHS
Task 1 | 0 | [6 empty] | 0 | <= | 6
Task 2 |  | 8 | [5 empty] | 8 | <= | 8
Task 3 |  |  | 8 |  |  |  |  | 8 | <= | 8
Task 4 |  |  |  | 0 |  |  |  | 0 | <= | 6
Task 5 |  |  |  |  | 0 |  |  | 0 | <= | 2
Task 6 | [5 empty] | 0 |  | 0 | <= | 4
Task 7 | [6 empty] | 4 | 4 | <= | 10
Path A | [7 empty] | 40 | <= | 40
Path B | [7 empty] | 36 | <= | 40
Path C | [7 empty] | 40 | <= | 40
Path D | [7 empty] | 40 | <= | 40

## Answer Report
Microsoft Excel 16.0 Answer Report
Worksheet: [ques13.xlsx]Q13 B
Report Created: 10/10/2022 5:22:25 PM
Result: Solver found a solution. All Constraints and optimality conditions are satisfied.
Solver Engine
Engine: Simplex LP
Solution Time: 0.031 Seconds.
Iterations: 7 Subproblems: 0
Solver Options
Max Time Unlimited, Iterations Unlimited, Precision 0.000001, Use Automatic Scaling
Max Subproblems Unlimited, Max Integer Sols Unlimited, Integer Tolerance 1%, Assume NonNegative
Objective Cell (Min)
| Cell | Name | Original Value | Final Value
| $L$6 | Min with crash cost $16,800.00 | 18600 | 18600
Variable Cells
| Cell | Name | Original Value | Final Value | Integer
| $B$3 |  | 0 | 0 | Contin
| $C$3 |  | 8 | 8 | Contin
| $D$3 |  | 8 | 8 | Contin
| $E$3 |  | 0 | 0 | Contin
| $F$3 |  | 0 | 0 | Contin
| $G$3 |  | 0 | 0 | Contin
| $H$3 |  | 4 | 4 | Contin
Constraints
| Cell | Name | Cell Value | Formula | Status | Slack
| $I$18 | Task 1 LHS | 0 | $I$18<=$K$18 | Not Binding | 6
| $I$19 | Task 2 LHS | 8 | $I$19<=$K$19 | Binding | 0
| $I$20 | Task 3 LHS | 8 | $I$20<=$K$20 | Binding | 0
| $I$21 | Task 4 LHS | 0 | $I$21<=$K$21 | Not Binding | 6
| $I$22 | Task 5 LHS | 0 | $I$22<=$K$22 | Not Binding | 2
| $I$23 | Task 6 LHS | 0 | $I$23<=$K$23 | Not Binding | 4
| $I$24 | Task 7 LHS | 4 | $I$24<=$K$24 | Not Binding | 6
| $I$25 | Path A LHS | 40 | $I$25<=$K$25 | Binding | 0
| $I$26 | Path B LHS | 36 | $I$26<=$K$26 | Not Binding | 4
| $I$27 | Path C LHS | 40 | $I$27<=$K$27 | Binding | 0
| $I$28 | Path D LHS | 40 | $I$28<=$K$28 | Binding | 0

## Sensitivity Report
Microsoft Excel 16.0 Sensitivity Report
Worksheet: [ques13.xlsx]Q13 B
Report Created: 10/10/2022 5:22:25 PM
Variable Cells
|  |  | Final | Reduced | Objective | Allowable | Allowable
| Cell | Name | Value | Cost | Coefficient | Increase | Decrease
| $B$3 |  | 0 | 40 | 100 | 1e+30 | 40
| $C$3 |  | 8 | 0 | 75 | 230 | 1e+30
| $D$3 |  | 8 | 0 | 120 | 185 | 1e+30
| $E$3 |  | 0 | 40 | 100 | 1e+30 | 40
| $F$3 |  | 0 | 0 | 140 | 1e+30 | 140
| $G$3 |  | 0 | 0 | 165 | 1e+30 | 165
| $H$3 |  | 4 | 0 | 60 | 40 | 60
Constraints
|  |  | Final | Shadow | Constraint | Allowable | Allowable
| Cell | Name | Value | Price | R.H. Side | Increase | Decrease
| $I$18 | Task 1 LHS | 0 | 0 | 6 | 1e+30 | 6
| $I$19 | Task 2 LHS | 8 | -230 | 8 | 0 | 2
| $I$20 | Task 3 LHS | 8 | -185 | 8 | 0 | 2
| $I$21 | Task 4 LHS | 0 | 0 | 6 | 1e+30 | 6
| $I$22 | Task 5 LHS | 0 | 0 | 2 | 1e+30 | 2
| $I$23 | Task 6 LHS | 0 | 0 | 4 | 1e+30 | 4
| $I$24 | Task 7 LHS | 4 | 0 | 10 | 1e+30 | 6
| $I$25 | Path A LHS | 40 | -60 | 40 | 4 | 6
| $I$26 | Path B LHS | 36 | 0 | 40 | 1e+30 | 4
| $I$27 | Path C LHS | 40 | -140 | 40 | 0 | 2
| $I$28 | Path D LHS | 40 | -165 | 40 | 0 | 4

## Limits Report
Microsoft Excel 16.0 Limits Report
Worksheet: [ques13.xlsx]Q13 B
Report Created: 10/10/2022 5:22:25 PM
Objective
| Cell | Name | Value
| $L$6 | Min with crash cost $16,800.00 | 18600
|  | Variable |  | Lower | Objective | Upper | Objective
| Cell | Name | Value | Limit | Result | Limit | Result
| $B$3 |  | 0 | 0 | 18600 | 6 | 19200
| $C$3 |  | 8 | 8 | 18600 | 8 | 18600
| $D$3 |  | 8 | 8 | 18600 | 8 | 18600
| $E$3 |  | 0 | 0 | 18600 | 6 | 19200
| $F$3 |  | 0 | 0 | 18600 | 2 | 18880
| $G$3 |  | 0 | 0 | 18600 | 4 | 19260
| $H$3 |  | 4 | 4 | 18600 | 10 | 18960